## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
DOMAIN NAME: | Fullstack Development
INTERN NAME: | Shreyash Deogirkar
PROJECT NAME: | Connectin
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-07-24
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-07-11 | Login/Register Data was not reflecting in the database | Authentication | Yes | Check MongoDB connection | The password changed and renentered | Myself | Solved
2 | 2024-07-14 | Navbar items were very close to each other | UI | No |  | Display Flex | Myself | Solved
3 | 2024-07-16 | Images were not uploading | Cloud | No | Check api key | I had used comma after the api key,after removing it worked | Myself | Solved
4 | 2024-07-16 | Images were still not uploading | Cloud | No | Check api security key | I didn’t know that I have to add api security key also | Myself | Solved
5 | 2024-07-20 | Not able to push on Github | Github push | Yes | check main branch | My main branch was master but now due to new update in the Github it gives code for main, I changed It to master then it worked | Myself | Solved
6 | 2024-07-21 | Not able to deploy on vercel | Deployment | No |  | I hadn't entered the environment variables file | Myself | Solved