## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 1 | 1 | 0 | 0 | 0 | 0
| Project title: | Connectin |  | Project Id: | IP-2949 | Project Manager: | Harshada Topale |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 1 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2024-07-25 | Project Team Lead: | ABC |  |  | Dependency | 1 | 0 | 1 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 3 |  |  |  |  | 3
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Data security and privacy concerns. | Potential loss of user trust and legal implications | Implement robust encryption and data protection measures; conduct regular security audits. | Project developer | Critical |  | Open | Risk
2 | Issue | Inconsistent user interface across different devices. | Poor user experience and lower user retention. | Conduct thorough testing on multiple devices and screen sizes; prioritize responsive design. | Project developer | High |  | Open | Assumption
3 | Dependency | Integration with third-party job listing APIs. | Delay in job listings appearing on the platform. | Establish agreements with API providers early in the project timeline; have backup API options. | Project developer | High |  | Open | Issue
4 | [8 empty] | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24