## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## PROJECT SCHEDULE
IAC INTERNSHIP PROGRAM 2024 FULL STACK DEVELOPMENT PROJECT SCHEDULE
DOCUMENT VERSION: 1.0
PROJECT NAME | ConnectIn
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | ConnectIn website
PROJECT SCOPE
PROJECT START DATE | 2024-07-05
PROJECT END DATE | 2024-07-22
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2024-07-05 | 2024-07-05 | 1 | COMPLETED
| 1.2 Recruit a team |  | 2024-07-06 | 2024-07-06 | 1 | COMPLETED
| 1.3 Create a project charter |  | 2024-07-07 | 2024-07-07 | 1 | COMPLETED
| 1.4 Requirement gathering |  | 2024-07-08 | 2024-07-08 | 1 | COMPLETED
| 2 Planning |  | 2024-07-08 | 2024-07-08 | 1 | COMPLETED
2.1 Setup the software required on laptop
2.2 Download the required dependencies
2.3 Choosing the tech-stack
3 Execution
| 3.1 Finalize design |  | 2024-07-09 | 2024-07-09 | 1 | COMPLETED
| 3.2 Build |  | 2024-07-09 | 2024-07-18 | 13 | COMPLETED
| 3.2.1 Features |  | 2024-07-09 | 2024-07-18 | 10
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2024-07-13 | 2024-07-15 | 3
Navigation bar with logo
Home
Jobs
My Network
Messaging
Notification
Sign in
| Sidebar |  | 2024-07-15 | 2024-07-16 | 2
Profile picture
Background picture
Post
Skills
Experience
| Feed |  | 2024-07-16 | 2024-07-17 | 2
Create Post
Add message
Upload Image
Timestamp-auto increment time
Post
Like
Comment
| News |  | 2024-07-18 | 2024-07-18 | 1
| 3.3 Testing |  | 2024-07-19 | 2024-07-20 | 2 | COMPLETED
3.3.1 Manual testing
3.3.2 Automation testing
| 3.4 Deployment |  | 2024-07-21 | 2024-07-21 | 1 | COMPLETED
| 4 Closure |  | 1900-01-21 | 2024-07-22 | 1 | COMPLETED